## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Web Based Stock Prediction Application
PROJECT MANAGER |  | Ram Vishal Gobind |  |  |  |  | DATE | [6 empty] | 2021-01-14
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Intiation Phase
1.1 | Stock Prediction Strategies | Vishal R | 2020-10-27 | 2020-10-28 | 1 | 100% | bar: WEEK 1 T to WEEK 1 W
1.2 | Gather Data Set from Yahoo Finance | Vishal R | 2020-10-27 | 2020-10-29 | 2 | 100% | bar: WEEK 1 T to WEEK 1 R
1.3 | Compare 15 Acadamic Journals | Vishal R | 2020-10-27 | 2020-10-31 | 4 | 100% | bar: WEEK 1 T to WEEK 2 M
1.4 | Identify Target Audience | Vishal R | 2020-10-27 | 2020-10-30 | 3 | 100% | bar: WEEK 1 T to WEEK 1 F
1.5 | Write Literature Review Report | Vishal R | 2020-11-02 | 2020-11-13 | 11 | 100% | bar: WEEK 2 M to WEEK 3 F
2 | Planning Phase
2.1 | Product Design Proposal | Vishal R | 2020-11-16 | 2020-11-20 | 4 | 100% | bar: WEEK 4 M to WEEK 4 F
2.2 | Prediction Model Exploration | Vishal R | 2020-11-16 | 2020-11-20 | 4 | 100% | bar: WEEK 4 M to WEEK 4 F
2.3 | Pre-process data set and build training dataset | Vishal R | 2020-11-18 | 2020-11-20 | 2 | 100% | bar: WEEK 4 W to WEEK 4 F
2.4 | System Requirements proposal | Vishal R | 2020-11-23 | 2020-11-27 | 4 | 100% | bar: WEEK 5 M to WEEK 5 F
2.5 | Product Software Archicture Design Proposal | Vishal R | 2020-11-30 | 2020-12-04 | 4 | 100% | bar: WEEK 6 M to WEEK 6 F
3 | Execution Phase
3.1 | Create Interactive UI with Shiny Package in R | Vishal R | 2020-12-07 | 2020-12-18 | 11 | 100% | bar: WEEK 7 M to WEEK 8 F
3.2 | Write R code for user inputs and visualizations | Vishal R | 2020-12-21 | 2020-12-25 | 4 | 100% | bar: WEEK 9 M to WEEK 9 F
3.3 | Write R code to plot line graphs to show trends under Analytics tab | Vishal R | 2020-12-21 | 2020-12-25 | 4 | 100% | bar: WEEK 9 M to WEEK 9 F
4 | Control and Closure Phase
4.1 | Acceptance Test | Vishal R | 2020-12-28 | 2020-12-29 | 1 | 100% | bar: WEEK 10 M to WEEK 10 T
4.2 | User evaluation plan - expert reviews and surveys | Vishal R | 2020-12-28 | 2020-12-30 | 2 | 100% | bar: WEEK 10 M to WEEK 10 W
4.3 | Risk Assesment of prototype to stakeholders | Vishal R | 2020-12-28 | 2020-12-30 | 2 | 100% | bar: WEEK 10 M to WEEK 10 W
4.4 | Customer relationship Management analysis | Vishal R | 2020-12-29 | 2021-01-01 | 2 | 100% | bar: WEEK 10 W to WEEK 10 F
4.5 | Product Marketing Strategy | Vishal R | 2021-01-04 | 2021-01-05 | 1 | 100% | bar: WEEK 11 M to WEEK 11 T
4.6 | Deploy program in Shiny and bug fixes | Vishal R | 2021-01-05 | 2021-01-08 | 3 | 100% | bar: WEEK 11 T to WEEK 11 W
4.7 | Write Final Report | Vishal R | 2021-01-06 | 2021-01-14 | 8 | 100% | bar: WEEK 11 W to WEEK 12 F